## Slide 1
FE CREDIT · IT DELIVERY FRAMEWORK
FE Credit IT Delivery Framework
Requirement → BRD → FSD → Test → UAT → Ship → Operations Support
Governed delivery with Agile/Scrum internal process

## Slide 2
Learning Objectives
IT Delivery Framework · Internal use only
2
1
Map the end-to-end IT delivery pipeline and mandatory gates
2
Align Scrum ceremonies with BRD / FSD / release governance
3
Clarify roles
Business, Dev, IT Ops, IT-Governance, IT-Security, GRC
4
Apply evidence chain from requirement intake to operations support

## Slide 3
End-to-End Delivery Pipeline
IT Delivery Framework · Internal use only
3
Governed pipeline with Agile/Scrum inside Build → SIT phases
Receive Req
BRD Gate
Triage & FSD
Sprint Build
SIT Test
UAT
Ship (CAB)
Ops Support

## Slide 4
Swimlane — Cross-Functional Delivery
IT Delivery Framework · Internal use only
4
No hand-off skips a lane — every phase has a named owner
Intake
Define
Design
Build
Test
Release
Operate
Business / Sponsor
Raise need
Write BRD + sign
UAT sign-off
Go-live approve
Confirm service
BA
Classify
Score BRD ≥80%
Author FSD
Refine stories
Support UAT
IT Product (PO)
Accept to triage
Prioritize backlog
Accept sprint
Release decision
Scrum / Dev
Design + tasks
Build + unit test
Fix SIT defects
Deploy
Hotfix / defect
QA
Test plan
Prep cases
Run SIT + regress
IT Ops / Assurance
Route ticket
Compliance routing
ARB / Security
CAB + verify
Monitor / hypercare

## Slide 5
Document Chain — Who Owns What
IT Delivery Framework · Internal use only
5
BRD (Business Requirements)
Business writes, Sponsor signs
FSD / FRD (Functional Spec)
BA + IT Product; derived from BRD
User Stories & Tasks
BA + Dev; traceable to FSD + BRD AC
Test Cases (SIT)
QA; mapped to acceptance criteria
UAT Scripts
Business; from BRD Section M
Change Request (CR)
IT Ops + IT-Governance (CAB)

## Slide 6
Three Lanes Operating Model
IT Delivery Framework · Internal use only
6
LANE 1 — DEMAND (Business + BA)
Define need → BRD → Sponsor → BA quality ≥80% → compliance routing → triage
LANE 2 — DELIVERY (IT Product + Dev + Ops)
FSD → Scrum sprints → SIT → UAT support → CAB → Ship → Hypercare
LANE 3 — ASSURANCE (IT-Gov + IT-Sec + GRC + Audit)
Architecture standards, security review, regulatory control, evidence pack

## Slide 7
Stakeholder Map
IT Delivery Framework · Internal use only
7
BUSINESS
Sponsor, requesters, UAT owners
IT DELIVERY
Ops Manager, BA, IT Product, Dev, Service Desk
IT-GOVERNANCE
CAB, ARB, CMDB, intake policy, change control
IT-SECURITY
Security architecture, IAM, exceptions, secure SDLC
GRC / LEGAL
Business compliance, contracts, collections
AUDIT / BOD
Evidence, material risk reporting

## Slide 8
Routing Rule — IT-Gov vs IT-Sec vs GRC
IT Delivery Framework · Internal use only
8
IT process & change control
IT-Governance
Security, access, data protection
IT-Security
Business & regulatory controls
Risk / GRC / Legal

## Slide 9
Phase 1 — Receive Requirement
IT Delivery Framework · Internal use only
9
1
Classify
standard IT ticket vs business change vs build request
2
Wrong bucket? → redirect to BRD (business must define first)
3
Assign
Service Desk | BA | IT Product

## Slide 10
Phase 2 — BRD & Quality Gate
IT Delivery Framework · Internal use only
10
Business drafts BRD → Sponsor (Director+) signs
1
Score ≥ 80% on quality rubric
2
Mandatory sections complete
3
Compliance Section N → auto-route GRC / IT-Security

## Slide 11
Phase 3 — IT Triage & Product Backlog
IT Delivery Framework · Internal use only
11
IT Product / Portfolio (≤5 business days)
1
Fit with strategy and capacity
2
Priority vs regulatory / revenue / risk
3
Decision
Approved for FSD | Deferred | Rejected (with reason)

## Slide 12
Agile/Scrum Inside the Pipeline
IT Delivery Framework · Internal use only
12
FSD feeds Product Backlog; Ship requires governance gates green
Product Backlog
Sprint Planning
Daily Build
SIT in Sprint
Sprint Review
UAT Window
Release CAB
Retro

## Slide 13
Phase 4 — FSD (Functional Specification / FRD)
IT Delivery Framework · Internal use only
13
BA + IT Product create FSD from accepted BRD
1
Functional flows mapped to BRD to-be state
2
Interface & system touchpoints (FE ONLINE, Finacle, LOS…)
3
Story breakdown with traceability ID → BRD-xxx
4
Non-functional
performance, security, audit trail

## Slide 14
Agile / Scrum — Where It Fits
IT Delivery Framework · Internal use only
14
Epic
= Accepted BRD
Feature
= FSD capability group
Story
= Implementable unit with AC
Task
= Dev work item

## Slide 15
Scrum Roles at FE Credit
IT Delivery Framework · Internal use only
15
Product Owner (IT Product)
Prioritizes backlog; accepts sprint output
Scrum Master (Dev Lead)
Facilitates ceremonies; removes blockers
Development Team
Build, unit test, support SIT fixes
BA
FSD, story refinement, UAT support
IT Ops Manager
Release discipline, CAB, hypercare
Business Sponsor
UAT accountability; go-live sign-off

## Slide 16
Backlog Hierarchy
IT Delivery Framework · Internal use only
16
1
Product Backlog (prioritized by IT Product)
2
└── Epic [BRD-2026-0042] POS lending visibility
3
└── Feature [FSD-3.2] Approval status API to POS
4
└── Story [US-101] Display pre-approved amount
5
└── Story [US-102] Handle expired pre-approval
6
└── Tasks
7
Every story must reference BRD acceptance criteria IDs

## Slide 17
Sprint Planning — Entry Checklist
IT Delivery Framework · Internal use only
17
✓
BRD accepted (score ≥ 80%) and linked
✓
FSD approved for this epic / feature
✓
GRC / Legal review complete (if flagged)
✓
IT-Security review complete (if Restricted / integration)
✓
Stories have clear AC and testable outcomes
✓
Team capacity confirmed; no conflicting release
✓
Ops aware of target UAT / deploy window

## Slide 18
Scrum Ceremonies Inside Delivery
IT Delivery Framework · Internal use only
18
Sprint N
≈ 2 weeks
Mon
Sprint Planning
Pull stories from FSD
Gate
Entry check
BRD + FSD linked, flags clear
Daily
Stand-up 15 min
Dev + SM + Ops
Wed
Mid-sprint
BA clarification, no scope creep
Fri
Code complete
Unit tests + SIT entry
Sprint N+1
Release sprint
Mon
SIT / QA
Regression, exit criteria
Wed
UAT window
Business tests BRD AC
Thu
Sprint Review
Demo to Sponsor delegate
Fri
Retrospective
Process improvement
Release week
Sprint boundary
Prep
Release readiness
Ops checklist + CAB
Go
Ship to prod
Deploy + verify
T+1
Hypercare
Handover to support

## Slide 19
Definition of Done — Development Team
IT Delivery Framework · Internal use only
19
✓
Code complete + peer review
✓
Unit tests pass; coverage per team standard
✓
Traceability: story → BRD AC → test case
✓
SIT-ready build deployed to test environment
✓
Release notes draft for Ops
✓
No open Critical/High defects for in-scope stories
✓
Security scan clean or exception recorded (IT-Security)

## Slide 20
Phase 5 — Test (SIT / QA)
IT Delivery Framework · Internal use only
20
QA executes SIT against FSD + BRD acceptance criteria
1
All in-scope test cases Pass
2
No open Sev-1 / Sev-2 defects
3
Test summary report attached to release record

## Slide 21
Phase 6 — UAT (Business Validation)
IT Delivery Framework · Internal use only
21
Business executes UAT scripts derived from BRD Section M
Given / When / Then — objective pass/fail
IT provides: UAT environment, test data, defect fixes
Business provides: testers, sign-off, edge-case validation
Gate: Sponsor (or delegate) signs UAT record
IT does NOT accept on behalf of business

## Slide 22
Phase 7 — Ship (Release to Production)
IT Delivery Framework · Internal use only
22
1
Release readiness review (Ops checklist)
2
Change Request submitted
linked BRD, FSD, UAT sign-off
3
CAB approval (IT-Governance)
IT-Security if flagged
4
Deploy via approved pipeline / runbook
5
Post-deploy verification (smoke test + monitoring)
6
CMDB / release record updated

## Slide 23
Phase 8 — Operations Support
IT Delivery Framework · Internal use only
23
HYPERCARE (T+1 to T+14)
1
Ops war room for Critical releases
2
Dev on standby for defects
3
Daily check with Business Sponsor
4
Service Desk knowledge article
5
Monitoring & alerting configured
6
Incident routing defined
7
Evidence pack closed for Audit (13 artifacts)

## Slide 24
Release Readiness — Go / No-Go
IT Delivery Framework · Internal use only
24
✓
BRD accepted and linked
✓
FSD complete; stories closed
✓
SIT exit criteria met
✓
UAT signed by Business Sponsor
✓
CAB approved (IT-Governance)
✓
IT-Security sign-off (if required)
✓
Rollback plan tested
✓
Comms & training complete (BRD Section K)
✓
Hypercare roster assigned

## Slide 25
Dual-Track: Governance + Agile Delivery
IT Delivery Framework · Internal use only
25
Governance & assurance — runs in parallel
BRD gate
GRC / Legal
IT-Security
ARB
CAB
Audit evidence
Agile delivery — Scrum (2-week sprints)
FSD
Sprint plan
Build
SIT
UAT
Ship
Hypercare
Governance runs in parallel — it does not wait for sprint end.
Ship only when BOTH tracks are green.

## Slide 26
Org Chart — Development & Operations
IT Delivery Framework · Internal use only
26
Delivery (build) and Operations (run) report into IT leadership — assurance is independent
CIO / IT Director
IT Product (PO)
BA Team
Scrum / Dev Team
QA / Test
IT Ops Manager
Service Desk
On-call / Night shift
Release / CAB coord
IT-Governance & Security
CAB / Change
IT-Security
GRC / Legal liaison

## Slide 27
Hard Gates — Non-Negotiable
IT Delivery Framework · Internal use only
27
1
No FSD / sprint work without accepted BRD (≥ 80%)
2
No story without traceability to BRD acceptance criteria
3
No UAT skip
business signs, not IT
4
No production deploy without CAB (IT-Governance)
5
No security bypass without IT-Security exception register
6
Email / chat is not intake for projects

## Slide 28
Audit Evidence Pack (per release)
IT Delivery Framework · Internal use only
28
1
BRD (+ versions) 2. BA scorecard 3. Sponsor approval
2
IT-Security sign-off (if flagged) 5. GRC/Legal (if flagged)
3
FSD linked to BRD 7. SIT results 8. UAT sign-off
4
CR + CAB approval 10. Deployment log 11. Post-deploy verify
5
Security scan / pen test (if required) 13. RCA (if incident)

## Slide 29
Key Metrics — Ops & Leadership Dashboard
IT Delivery Framework · Internal use only
29
BRD first-pass acceptance rate
Target ≥ 60%
BRD
triage decision time Target < 5 days
Deployments without linked BRD
Target 0
UAT sign-off before production
Target 100%
Emergency prod changes / month
Target ≤ 2
Open IT-Security prod exceptions
Target 0

## Slide 30
Escalation Paths
IT Delivery Framework · Internal use only
30
Skip BRD pressure
Ops → IT-Governance policy → IT Director
GRC hold + deploy rush
Document hold → GRC Manager → no deploy
Security review open
Ops blocks CR → IT-Security lead
Scope dispute
BA → IT Product → Sponsor
CAB rejection
IT-Governance → IT Product → Sponsor
Material incident
IT-Security IR → CIO → EXCO / BOD

## Slide 31
Summary
IT Delivery Framework · Internal use only
31
DEMAND: Business defines in BRD — IT does not guess rules
DELIVER: Scrum builds from FSD with traceability to BRD
ASSURE: IT-Governance + IT-Security + GRC run in parallel
SHIP: CAB + UAT — then hypercare → BAU support
Docs: docs/12-it-operations-stakeholder-framework.md
docs/11-operations-manager-checklist.md

## Slide 32
Next Steps
IT Delivery Framework · Internal use only
32
1
Publish framework on Confluence (FECBRD space)
2
Configure Jira
Epic = BRD, Feature = FSD, link fields mandatory
3
Train dev leads on sprint planning gate checklist
4
Align CAB charter with IT-Governance + IT-Security
5
Weekly Ops metrics to IT leadership