## Slide 1: FE Credit IT Delivery Framework
Requirement → BRD → FSD → Test → UAT → Ship → Operations Support
Governed delivery with Agile/Scrum internal process

## Slide 2: Learning Objectives
• Map the end-to-end IT delivery pipeline and mandatory gates
• Align Scrum ceremonies with BRD / FSD / release governance
• Clarify roles: Business, Dev, IT Ops, IT-Governance, IT-Security, GRC
• Apply evidence chain from requirement intake to operations support

## Slide 3: End-to-End Delivery Pipeline
Governed pipeline with Agile/Scrum inside Build → SIT phases
Receive
Req
BRD
Gate
Triage
& FSD
Sprint
Build
SIT
Test
UAT
Ship
(CAB)
Ops
Support

## Slide 4: Document Chain — Who Owns What
BRD (Business Requirements) → Business writes, Sponsor signs
FSD / FRD (Functional Spec) → BA + IT Product; derived from BRD
User Stories & Tasks → BA + Dev; traceable to FSD + BRD AC
Test Cases (SIT) → QA; mapped to acceptance criteria
UAT Scripts → Business; from BRD Section M
Change Request (CR) → IT Ops + IT-Governance (CAB)
Rule: each document links upward — full traceability for Audit

## Slide 5: Three Lanes Operating Model
LANE 1 — DEMAND (Business + BA)
Define need → BRD → Sponsor → BA quality ≥80% → compliance routing → triage
LANE 2 — DELIVERY (IT Product + Dev + Ops)
FSD → Scrum sprints → SIT → UAT support → CAB → Ship → Hypercare
LANE 3 — ASSURANCE (IT-Gov + IT-Sec + GRC + Audit)
Architecture standards, security review, regulatory control, evidence pack

## Slide 6: Stakeholder Map
BUSINESS Sponsor, requesters, UAT owners
IT DELIVERY Ops Manager, BA, IT Product, Dev, Service Desk
IT-GOVERNANCE CAB, ARB, CMDB, intake policy, change control
IT-SECURITY Security architecture, IAM, exceptions, secure SDLC
GRC / LEGAL Business compliance, contracts, collections
AUDIT / BOD Evidence, material risk reporting

## Slide 7: Routing Rule — IT-Gov vs IT-Sec vs GRC
IT process & change control → IT-Governance
Security, access, data protection → IT-Security
Business & regulatory controls → Risk / GRC / Legal
All three may apply to one BRD — route early, run in parallel

## Slide 8: Phase 1 — Receive Requirement
Channel: ServiceNow / Jira BRD catalog (not email for projects)
1. Classify: standard IT ticket vs business change vs build request
2. Wrong bucket? → redirect to BRD (business must define first)
3. Assign: Service Desk | BA | IT Product
Ops Manager: enforce one front door; log informal requests

## Slide 9: Phase 2 — BRD & Quality Gate
Business drafts BRD → Sponsor (Director+) signs
BA quality review (≤2 business days)
• Score ≥ 80% on quality rubric
• Mandatory sections complete
• Compliance Section N → auto-route GRC / IT-Security
Outcome: Accepted to triage | Returned | Deferred

## Slide 10: Phase 3 — IT Triage & Product Backlog
IT Product / Portfolio (≤5 business days)
• Fit with strategy and capacity
• Priority vs regulatory / revenue / risk
• Decision: Approved for FSD | Deferred | Rejected (with reason)
Approved BRD → Product Backlog item (Epic) in Jira

## Slide 11: Agile/Scrum Inside the Pipeline
FSD feeds Product Backlog; Ship requires governance gates green
Product
Backlog
Sprint
Planning
Daily
Build
SIT in
Sprint
Sprint
Review
UAT
Window
Release
CAB
Retro

## Slide 12: Phase 4 — FSD (Functional Specification / FRD)
BA + IT Product create FSD from accepted BRD
FSD contains:
• Functional flows mapped to BRD to-be state
• Interface & system touchpoints (FE ONLINE, Finacle, LOS…)
• Story breakdown with traceability ID → BRD-xxx
• Non-functional: performance, security, audit trail
Gate: no sprint planning without FSD linked to BRD

## Slide 13: Agile / Scrum — Where It Fits
Governance gates are OUTSIDE the sprint (BRD, FSD, CAB).
Scrum runs INSIDE build & test phases.
Epic = Accepted BRD
Feature = FSD capability group
Story = Implementable unit with AC
Task = Dev work item
2-week sprints typical; release may span 1–2 sprints + UAT window

## Slide 14: Scrum Roles at FE Credit
Product Owner (IT Product) Prioritizes backlog; accepts sprint output
Scrum Master (Dev Lead) Facilitates ceremonies; removes blockers
Development Team Build, unit test, support SIT fixes
BA FSD, story refinement, UAT support
IT Ops Manager Release discipline, CAB, hypercare
Business Sponsor UAT accountability; go-live sign-off

## Slide 15: Backlog Hierarchy
Product Backlog (prioritized by IT Product)
└── Epic [BRD-2026-0042] POS lending visibility
└── Feature [FSD-3.2] Approval status API to POS
└── Story [US-101] Display pre-approved amount
└── Story [US-102] Handle expired pre-approval
└── Tasks: dev, test, docs
Every story must reference BRD acceptance criteria IDs

## Slide 16: Sprint Planning — Entry Checklist
☐ BRD accepted (score ≥ 80%) and linked
☐ FSD approved for this epic / feature
☐ GRC / Legal review complete (if flagged)
☐ IT-Security review complete (if Restricted / integration)
☐ Stories have clear AC and testable outcomes
☐ Team capacity confirmed; no conflicting release
☐ Ops aware of target UAT / deploy window

## Slide 17: Scrum Ceremonies Inside Delivery
SPRINT N (typically 2 weeks)
──────────────────────────────────────────────────
Mon Sprint Planning Pull stories from FSD → sprint backlog
Gate: BRD accepted, FSD linked, flags clear
Daily Stand-up (15 min) Dev + SM + Ops (deploy blockers)
Wed Mid-sprint BA clarification; no new scope without change
Fri Code complete Unit tests + SIT entry
──────────────────────────────────────────────────
SPRINT N+1 or Release sprint
Mon SIT / QA regression QA exit criteria
Wed UAT window Business tests BRD acceptance criteria
Thu Sprint Review Demo to Sponsor delegate
Fri Retrospective Process improvement
──────────────────────────────────────────────────
RELEASE WEEK (may align with sprint boundary)
Release readiness Ops checklist + CAB (IT-Governance)
Ship to production Deploy + verify + hypercare handover

## Slide 18: Definition of Done — Development Team
☐ Code complete + peer review
☐ Unit tests pass; coverage per team standard
☐ Traceability: story → BRD AC → test case
☐ SIT-ready build deployed to test environment
☐ Release notes draft for Ops
☐ No open Critical/High defects for in-scope stories
☐ Security scan clean or exception recorded (IT-Security)

## Slide 19: Phase 5 — Test (SIT / QA)
QA executes SIT against FSD + BRD acceptance criteria
Flow: Unit tests (Dev) → SIT (QA) → Regression → Defect fix loop
Exit criteria:
• All in-scope test cases Pass
• No open Sev-1 / Sev-2 defects
• Test summary report attached to release record
Then → UAT environment ready for Business

## Slide 20: Phase 6 — UAT (Business Validation)
Business executes UAT scripts derived from BRD Section M
Given / When / Then — objective pass/fail
IT provides: UAT environment, test data, defect fixes
Business provides: testers, sign-off, edge-case validation
Gate: Sponsor (or delegate) signs UAT record
IT does NOT accept on behalf of business

## Slide 21: Phase 7 — Ship (Release to Production)
1. Release readiness review (Ops checklist)
2. Change Request submitted — linked BRD, FSD, UAT sign-off
3. CAB approval (IT-Governance) — IT-Security if flagged
4. Deploy via approved pipeline / runbook
5. Post-deploy verification (smoke test + monitoring)
6. CMDB / release record updated
Hard gate: no production deploy without UAT + CAB

## Slide 22: Phase 8 — Operations Support
HYPERCARE (T+1 to T+14)
• Ops war room for Critical releases
• Dev on standby for defects
• Daily check with Business Sponsor
BAU HANDOVER
• Service Desk knowledge article
• Monitoring & alerting configured
• Incident routing defined
• Evidence pack closed for Audit (13 artifacts)

## Slide 23: Release Readiness — Go / No-Go
☐ BRD accepted and linked
☐ FSD complete; stories closed
☐ SIT exit criteria met
☐ UAT signed by Business Sponsor
☐ CAB approved (IT-Governance)
☐ IT-Security sign-off (if required)
☐ Rollback plan tested
☐ Comms & training complete (BRD Section K)
☐ Hypercare roster assigned

## Slide 24: Dual-Track: Governance + Agile Delivery
Governance & assurance (parallel)
BRD gate
GRC / Legal
IT-Security
ARB
CAB
Audit evidence
Agile delivery (Scrum)
FSD
Sprint plan
Build
SIT
UAT
Ship
Hypercare
Governance track can run in parallel — it does not wait for sprint end.
Delivery track runs in 2-week sprints; Ship only when BOTH tracks are green.

## Slide 25: Hard Gates — Non-Negotiable
1. No FSD / sprint work without accepted BRD (≥ 80%)
2. No story without traceability to BRD acceptance criteria
3. No UAT skip — business signs, not IT
4. No production deploy without CAB (IT-Governance)
5. No security bypass without IT-Security exception register
6. Email / chat is not intake for projects

## Slide 26: Audit Evidence Pack (per release)
1. BRD (+ versions) 2. BA scorecard 3. Sponsor approval
4. IT-Security sign-off (if flagged) 5. GRC/Legal (if flagged)
6. FSD linked to BRD 7. SIT results 8. UAT sign-off
9. CR + CAB approval 10. Deployment log 11. Post-deploy verify
12. Security scan / pen test (if required) 13. RCA (if incident)

## Slide 27: Key Metrics — Ops & Leadership Dashboard
BRD first-pass acceptance rate Target ≥ 60%
BRD → triage decision time Target < 5 days
Deployments without linked BRD Target 0
UAT sign-off before production Target 100%
Emergency prod changes / month Target ≤ 2
Open IT-Security prod exceptions Target 0

## Slide 28: Escalation Paths
Skip BRD pressure → Ops → IT-Governance policy → IT Director
GRC hold + deploy rush → Document hold → GRC Manager → no deploy
Security review open → Ops blocks CR → IT-Security lead
Scope dispute → BA → IT Product → Sponsor
CAB rejection → IT-Governance → IT Product → Sponsor
Material incident → IT-Security IR → CIO → EXCO / BOD

## Slide 29: Summary
DEMAND: Business defines in BRD — IT does not guess rules
DELIVER: Scrum builds from FSD with traceability to BRD
ASSURE: IT-Governance + IT-Security + GRC run in parallel
SHIP: CAB + UAT — then hypercare → BAU support
Docs: docs/12-it-operations-stakeholder-framework.md
docs/11-operations-manager-checklist.md

## Slide 30: Next Steps
• Publish framework on Confluence (FECBRD space)
• Configure Jira: Epic = BRD, Feature = FSD, link fields mandatory
• Train dev leads on sprint planning gate checklist
• Align CAB charter with IT-Governance + IT-Security
• Weekly Ops metrics to IT leadership